## Slide 1: Public Access: Update on Progress
National Science Foundation
April 2, 2014

## Slide 2: OSTP Memo, 2/22/2013
  Within six months, agencies will develop plans to increase public access to scientific publications and scientific data in digital formats, consistent with their missions and existing law
  Underlying principles:
    Maintains the importance of peer review and the role of publishers
    Calls for collaboration among agencies and stakeholder groups
    Does not specify a funding strategy, allowing for experimentation
    Does not specify a technical approach but does encourage leveraging existing archives

## Slide 3: Where are we?
Plan (still not public)
  Submitted the draft, August 22, 2013
    NSF Steering Committee
    Working groups on publications and data
    Interagency working groups on publications and data
    Public input, May 14-17, 2013
  Received comments, February 20, 2014
  Revised document, May 20, 2014
October 2013-Present
  Technical studies to assess feasibility of solutions for system integration (DIS/DIAS/DAS/CIO/OD)
  Policy implications (Policy/OGC)
  Internal/external communications

## Slide 4: The draft plan outlines a framework.
Recognize the diversity of science NSF supports
  Take into account multiple agency funding
  Extensible to many kinds of research outputs
Minimize burden on awardees, investigators, and program and administrative staff
Build on existing practice to the extent possible
Leverage existing infrastructure and infrastructure components
Accommodate change

## Slide 5: More considerations
Managing data is harder than dealing with publications.
The plan would have to unfold over a period of years (and funding cycles).
Change will touch almost every corner of the Foundation.
Communicating with program staff and research communities is critical.

## Slide 6: Going forward
Policy: Announce the policy and alert the communities to upcoming changes to PAPPG using existing Federal-wide procedures
Technology: Start with publications to figure out how the external/internal integration will work.
  Reporting
  Pre/post-award management systems
  Award search
  Website
Communications: Ways to engage primarily around data:
  Program staff
  Research communities
  Public

## Slide 7: We have a small budget.
Systems development (DIS/DIAS)
Repository partnership(s) (external)
Communications and outreach
  National Academies/NRC forum
  Program support for data-related activities

## Slide 8: Your help
Where can we embed activities to advance public access concerns? What external groups might be partners? How can publishers and professional societies help?
How well is the current DMP requirement working?
Pilot activities in your communities?
  Technical
    Metadata
    Citation
    Identifiers
    Repository standards
  Training and mentoring around data
  Appraisal, retention, deaccessioning
What questions will you have?

## Slide 9
Thank you!
Amy Friedlander
afriedla@nsf.gov
Clifford Gabriel
cjgabrie@nsf.gov
Joanne Tornow
jtornow@nsf.gov

## Slide 10
CREDITS
Copyrighted material used under Fair Use. If you are the
copyright holder and believe your material has been used unfairly,
or if you have any suggestions, feedback, or support, please
contact ciseitsupport@nsf.gov
Except where otherwise indicated, permission is granted to copy,
distribute, and/or modify all images in this document under the
terms of the GNU Free Documentation license, Version 1.2 or any
later version published by the Free Software Foundation; with no
Invariant Sections, no Front-Cover Texts, and no Back-Cover
Texts. A copy of the license is included in the section entitled
“GNU Free Documentation license” at
http://commons.wikimedia.org/wiki/
Commons:GNU_Free_Documentation_License
The inclusion of a logo does not express or imply the
endorsement by NSF of the entities' products, services, or
enterprises.