# Housing and Warehouse Facilities at McMurdo Station Antarctica

## November 2003

# Introduction

This report responds to a request contained in the House Committee on Appropriations’ Report 107-740, accompanying the FY 2003 Appropriations Bill for Veterans Affairs and Housing and Urban Development, and Independent Agencies:

…the Committee is aware of the pressing need to provide both upgraded living facilities and adequate, indoor storage facilities at NSF’s McMurdo Station in Antarctica. In this regard, the Committee requests that the OPP prepare and deliver to the Committee at the earliest date possible a report outlining the work that needs to be performed to upgrade these facilities as well as the estimated short- and long-term costs involved with such upgrades. The report should detail whether such facilities would be new construction or retrofits or upgrades to existing facilities. Upon completion and delivery of such report, OPP may utilize available resources provided herein to begin planning, design, pre-construction and/or construction activities related to such necessary upgrades.

# Background

The general area of McMurdo Station, at a latitude of 77 1' South and longitude of 166 0' East, was first visited by James Clark Ross, a British explorer, in 1841.  Ross Island, where McMurdo is located, is named for this early explorer even though he did not make landfall on the island.  The station is named in honor of Archibald McMurdo, a lieutenant on the HMS Terror, one of the two ships used in Ross’s Antarctic expedition.  The next visitors to this area, and the first to land on Ross Island, were members of Scott’s Discovery Expedition in January 1902.  The island was next seen by Shackleton’s British Antarctic Expedition in 1908 and by Scott again in 1911.  Shackleton’s Endurance-Aurora Expedition used Ross Island as a staging area for the British Imperial Trans-Antarctic Expedition in 1914.

McMurdo Station, originally named Naval Air Facility McMurdo, was established in December 1955 in preparation for the extensive scientific activities of the International Geophysical Year (IGY).  Over the past 47 years, the station has grown from the original 30 buildings to the present community of over 90 buildings with utilities, about 12 million gallons of fuels storage, communications and infrastructure to support year-round presence with populations reaching 1,200 people in the summer season.  McMurdo Station is the logistics hub for the National Science Foundation’s (NSF) United States Antarctic Program (USAP).  The station supports six months of intra- and inter-continental aircraft operations and annual resupply of fuel and supplies by a tanker and a cargo vessel.

In 1972, the White House transferred responsibility for managing and funding the U.S. Antarctic Program, including the infrastructure at the three Antarctic stations (McMurdo, Amundsen-Scott South Pole, and Palmer) and Christchurch, New Zealand, from the U.S. Navy to the NSF.  Since the 1970’s, the size and scope of the science programs has increased dramatically.  The Office of Polar Programs (OPP), the office to which NSF delegated responsibility for the USAP, has replaced or upgraded many facilities but is still faced with legacy structures, many dating back to the 1960’s.  OPP prepared long-range development plans for McMurdo Station in 1979 and 1995 and is currently completing an update of the 1995 plan.  The 1979 plan focused on consolidating functions, making improvements to science facilities, and establishing city-zoning areas for future growth.  The 1979 plan provided the vision for development of McMurdo Station from a 1950’s and 1960’s temporary logistics camp to a science-based campus environment.  Because of growth in the USAP program, changing operational requirements, and a strong awareness for the need to prioritize future construction projects, a new Long Range Development Plan was prepared in 1995.  The 1995 plan focused on consolidating functions, replacing inefficient buildings, improving functionality, and reducing the overall “foot print” of the station.  In many ways the 1995 plan was more of a facilities replacement plan than a city development plan.   The priorities established in this plan served as the blueprint for improving the USAP infrastructure and services to scientists.

Both plans were used to guide and prioritize facility and utility infrastructure development.  During the 1980’s and early 1990’s, NSF implemented many of the improvements outlined in the 1979 plan:  11 new dormitories, a new heavy vehicle maintenance facility, and the Crary Science and Engineering Center were all constructed during this time period.  Of the top 10 priority projects identified in the 1995 plan, four have been completed: the mechanical equipment center was replaced; food preparation facilities and the dining room were remodeled; bulk fuel tanks were replaced; and three dormitory buildings were remodeled.  In addition, three major projects not identified when the plan was developed have also been completed or are under construction:  the Waste Water Treatment Facility, which went into operation in February 2003, was funded to prevent adverse impacts to the McMurdo area environment; HF radio transmitter site and the Joint Space Operations Center were required to facilitate communications and IT upgrades.

Even with these substantial investments in facility infrastructure over the last 23 years, the average age of the 92 buildings at McMurdo Station exceeds 20 years. The power plant is reaching the end of its useful life.  Safety issues have been identified in shop facilities and the medical clinic.  Many residents live in inadequate housing.  Warehousing functions are spread around the station in more than 25 buildings.  The energy efficiency of most buildings needs significant improvement.  Immediate plans on housing and warehousing include:

- Constructing two 100-person, single-room housing buildings;

- Renovating two existing buildings to create additional single rooms; and

- Constructing two new buildings – unheated and heated -- thus consolidating warehousing.  These buildings would replace space used currently in more than 25 different locations.

# Next-Generation Plan

In November 2001, NSF selected Daniel, Mann, Johnson, & Mendenhall (DMJM), a noted architectural firm, to update and expand the 1995 plan.  The firm was tasked to assess the current status and priority of facility requirements identified in the 1995 plan, to evaluate the station as a whole, and to develop a comprehensive document that will guide investment decisions at McMurdo Station for the next five to 10 years.  A copy of the McMurdo Station Long-Range Development Plan, completed in June 2003, is attached for reference.  A separate copy of the Plan’s Summary is also included separately.  The Priority-One Projects could be implemented in six years at a cost of $62.6 million, taking USAP logistical constraints into account.  Table 1 summarizes the annual implementation cost in FY03 dollars.

It is important to recognize that these plans are continually updated, often due to natural events that cause the USAP to reconsider current operations and way of doing business.  For example, the 8-million gallon fuel storage was not in the 1995 plan as one of the high priority projects, but was added in the past year.  The difficult ice conditions in the McMurdo Sound area  and the concomitant difficulties getting fuel delivered to McMurdo made it clear that the capability to store enough fuel to sustain the stations in McMurdo and the South Pole for two years, rather than one, was a high, if not critical, priority.

NSF’s current top priority is upgrading the power plant.  In addition to being obsolete, the power plant has been identified as the most critical single point failure risk to the USAP.  In view of the threat to safety that loss of electricity and heating would pose, FY 2003 funds have already been invested to initiate this project.

The Subcommittee has highlighted the need for improved housing and warehouse facilities, and the new NSF/OPP Long Range Plan assigns high priority to both, as is discussed below.

Housing

As noted in the Background, McMurdo Station is the gateway to the South Pole and many Antarctic field camps.  It also hosts a broad range of scientific activity, much of it facilitated by the state-of-the-art Crary Laboratory.  Grantees from 75 U.S. universities and research institutions, staff from several Government agencies and employees of various support companies, including the following, are housed for periods varying from one day to over one year.

| - 75 U.S. universities or laboratories | - U. S. Coast Guard |
| --- | --- |
| - National Science Foundation | - Raytheon Polar Services Company |
| - NOAA | - Petroleum Helicopters, Inc. |
| - USGS | - Space Mark, Inc. |
| - DOE | - New Zealand Defense Personnel |
| - Smithsonian | - Ken Borek Air |
| - Collaborating International Scientists | - NANA Services |
| - New York Air National Guard (109th) | - Royal New Zealand Air Force |
| - DOD Support Personnel |  |

The age and condition of housing at McMurdo varies from new construction to newly remodeled to just functional. There are currently 585 rooms in 16 buildings with a total bed capacity of 1,300 (Table 2).  Except for one bunkroom with 28 beds, the number of beds per room varies from 1 to 4.  The greater majority of rooms are designated as double occupancy.  As noted in Table 3, until additional housing is made available, NSF has established a standard of no more than two persons per room, except for transient personnel who are housed in up to 4 persons per room or in the 28-person bunkroom.  During periods of peak activity (late October, early November, January and February), however, personnel needing housing for less than 30 days may be housed 3 or 4 to a room.  With the exception of housing for the 109th there are only 25 designated single rooms in the current housing inventory.   The 109th’s housing allocation of 93 rooms for 113 staff provides 73 single occupancy rooms and is required to meet DOD flight crew rest criteria (the balance of 109th personnel, approximately 40 people, are housed two persons per room).  Table 4 summarizes McMurdo Station population by week for the last three summer seasons.  It should be noted that even with careful planning, restricted activities, and limited visitors, the NSF’s stated occupancy standards of a maximum of two people per room is exceeded for over 30% of the summer season weeks

During the winter season, March to August, adequate housing exists to assign single occupancy to all winter over staff.  This is a great morale benefit during the long winter months of isolation.  A desirable goal is to achieve single rooms for 40% of the summer population by 2008.  This goal will greatly improve the quality of life on station and will enhance the recruitment and retention of high quality support staff.   Successful support of scientific research is highly dependent on retaining qualified staff to support science, IT, station operations, air traffic control, and many other areas of specialized support.    This single occupancy goal, however, is still far below housing standard for private industry at remote locations (e.g., in Alaska and at off-shore drilling platforms).  NSF intends to continuously re-evaluate its ability to provide higher percentages of single rooms to USAP participants.

Excessive occupancy per room significantly reduces workforce efficiency and quality of life, but several other factors are also important.  Bathroom location is the second most important consideration.  Buildings 206, 207, 208, and 209 are the only housing spaces with semi-private bathrooms; two two-person bedrooms share one bathroom.  All other housing buildings have one or more centrally located community bathrooms.  Each housing building has one or more lounges, and most have laundry facilities.  All housing spaces are non-smoking, but three buildings have smoking lounges.   Assignment or selection of roommates is also a strong quality of life consideration for most individuals.   Factors such as nonsmoker/smoker, night/day shift, duration of deployment, age, compatibility with roommates, job assignment, and social habits also have a major impact on the quality of life in shared spaces.

Another housing consideration is building location.  Two of the lowest quality housing facilities (buildings 166 and 188) and NSF housing (building 125 and 137) are located in areas designated in the McMurdo Long Range Development Plan (MLRDP) as light industrial/science support.   As shown in Executive Summary of the MLRDP buildings 125, 137 and 188 will be removed and building 166 will be remodeled for science and science support offices.  The MLRDP also identifies the first floor of building 155 (19 bedrooms/71 beds) as the future location for the McMurdo Station Medical Clinic.  Upgrading and relocating the Medical Clinic is a high priority.  Implementation of these science, science support and medical upgrades will first require construction of 194 new housing spaces to maintain the current population capacity of the station.

In December 2001, OPP evaluated various housing configurations for applicability at McMurdo Station.  Knowing that the current double occupancy standard impacts the USAP’s ability to recruit and retain highly qualified participants and that the standards for private sector camps in remote locations is single occupancy with shared bathrooms, NSF is planning that future housing facilities should be designed for single occupancy, but configured with centralized bathroom facilities.   This will help minimize cost both in construction and future maintenance.

The highest priority housing related project in the MLRDP is constructing two 100-person, single-room housing buildings at an estimated cost of $8 million.   With the completion of these two new housing buildings approximately 30% of the station population of 1,200 will have single rooms.  Other activities that will help meet the single occupancy goal are:

- Demolish Building 188, and replace with 42 new single bedrooms.

- Convert the first floor housing in Building 155 to the station Medical Clinic and construct 71 new single bedrooms.

To meet the 40% single occupancy goal, an additional 100-person housing building will be needed.

# Warehousing

Warehousing at McMurdo Station can be grouped into four functional categories: heated, unheated, food storage, and specialty items.   Existing locations and square footage for each category are listed in Table 5.  In addition to the warehousing, there is approximately 20,000 square feet of open storage for bulk and crated materials.  Multiple storage locations and open storage results in poor materials control, inefficient operations, damaged and lost materials, and excessive labor to dig out and repackage materials buried in the snow.   The MLRDP recommends consolidating all non-specialty warehousing functions, both enclosed and open, in three facilities: Consolidated Heated Central Warehouse, Consolidated Unheated Central Warehouse and Consolidated Food Storage Warehouse.

The MLRDP lists both the heated and unheated consolidated warehouses as immediate requirements.  Because of the amount of lost and damaged materials and the labor to clear snow and repackage materials each year, the unheated warehouse is considered a higher priority. It is envisioned to be a 40,000 square foot building with high density racking and shelving systems that is approximately three times more efficient and the current unheated warehouses and open storage areas.   The estimated cost is $5.0 million.    The heated central warehouse is envisioned to be a 30,000 square foot building, again with high volume racking and shelving systems, and is estimated to cost $7.1 million.  The consolidated food storage warehouse is a priority 2 project and estimated to cost $4.7 million.

Table 1.  Annual Cost Schedule for Priority 1 Projects -- assuming logistics, rather than funding constrain schedule

##### Labor, Logistics and Equipment Limited

(Millions of Dollars)

| Project | FY04 | FY05 | FY06 | FY07 | FY08 | FY09 | Estimate |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Power & Water Plant Upgrade | 6.0 | 1.2 | 2.0 | 0.4 |  |  | 9.6 |
| Mogas Tank & Fueling Station | 1.4 | 0.4 |  |  |  |  | 1.8 |
| Expand Waste Heat Loop | 0.1 | 1.4 | 0.4 | 0.1 |  |  | 2.0 |
| Trades Shop | 0.7 | 4.1 | 1.0 | 1.0 |  |  | 6.8 |
| Consolidated Unheated Central Warehouse | 4.6 | 0.4 |  |  |  |  | 5.0 |
| Two Housing Units (200 single rooms) | 0.5 | 2.5 | 0.5 | 1.0 | 0.5 |  | 8.0 |
| Science & Facilities Carpentry Shop | 0.4 | 2.0 | 0.3 | 1.2 |  |  | 3.9 |
| Utility System Upgrade | 1.1 | 1.0 | 1.0 | 0.3 | 0.1 |  | 3.5 |
| Phase II Science Support Center |  | 0.2 | 2.8 | 1.4 | 0.3 |  | 4.7 |
| Consolidated Heated Central Warehouse |  |  | 0.7 | 4.0 | 2.1 | 0.3 | 7.1 |
| Medical Upgrade |  |  | 0.1 | 2.4 | 1.5 | 0.2 | 4.2 |
| 8 M Gallon Fuel Storage | 2.5 | 3.0 | 0.5 |  |  |  | 6.0 |
| Annual Budget | 17.3 | 16.2 | 12.3 | 11.8 | 4.5 | 0.5 | 62.6 |

Table 2.  McMurdo Station Housing Summary

|  | Building Number |  | Number of Rooms | Number of Beds | Date of Construction |
| --- | --- | --- | --- | --- | --- |
| 1 | 201 |  | 27 | 54 | 1979 |
| 2 | 202 |  | 27 | 54 | 1979 |
| 3 | 203A |  | 27 | 54 | 1980 |
| 4 | 203B |  | 25 | 50 | 1980 |
| 5 | 203C |  | 27 | 54 | 1980 |
| 6 | 206 |  | 66 | 132 | 1986 |
| 7 | 207 |  | 64 | 128 | 1987 |
| 8 | 208 |  | 64 | 128 | 1988 |
| 9 | 209 |  | 64 | 128 | 1989 |
| 10 | 210 |  | 35 | 70 | 1994 |
| 11 | 211 |  | 39 | 78 | 1994 |
| 12 | 188 |  | 21 | 42 | 1976 |
| 13 | 166 |  | 21 | 42 | 1968 |
| 13a | 166 (Bunkroom) |  | 1 | 28 | 1968 |
| 14 | 155 1st Floor |  | 19 | 71 | 1969 |
| 14a | 155, 2nd floor |  | 47 | 176 | 1969 |
| 15 | 125 |  | 6 | 6 | 1963 |
| 16 | 137 |  | 5 | 5 | 1967 |
|  | ###### TOTAL |  | 585 | 1300 |  |

Table 3.  McMurdo Station Housing Standards and Goals1

| Standard | Goal |
| --- | --- |
| Maximum occupants per room | 2 |
| Minimum area for two occupants | 170 sq ft |
| Minimum area for one occupant. | 80 sq ft |
| Fire suppression and detection | Per NFPA2 |
| Exiting standards | Per NFPA |
| 40% single occupancy | By 2008 |

1Goals established in 2000-2001.  Before this, four people per room was routine.

2NFPA: National Fire Protection Association

Table 5.  Existing McMurdo Station Warehousing Summary

| Building | Storage Area (sq. ft.) | Admin. Area (sq. ft.) | Heated | Contents |
| --- | --- | --- | --- | --- |
| ### Heated Warehouse Functions |  |  |  |  |
| 87 | 4,900 | 0 | No | FEMC |
| 121 (floor 2) | 3,600 | 200 | Yes | Electrical |
| 136 | 2,500 | 300 | Yes | UT & Plumbing |
| 140 | 2,500 | 1,500 | Yes | Central Supply |
| 141 | 3,800 | 0 | Yes | Electrical |
| 191/191A | 3,300 | 350 | Yes | FEMC |
| 637 | 1,000 | 0 | No | FEMC |
| 174 | 5,800 | 0 | Yes | DNF, EH&S |
| Subtotal | 27,400 | 2,350 |  |  |
| ### Unheated Warehouse Functions |  |  |  |  |
| 340 | 4,000 | 0 | No | Special Projects |
| 341 | 4,000 | 0 | No | UT, Plumbing |
| 342 | 4,000 | 0 | No | Central Supply |
| Milvans | 22,000 | 0 | No | General Supply |
| Open | 20,000 | 0 | No | Special Projects |
| Subtotal | 54,000 |  |  |  |
| ### Food Storage |  |  |  |  |
| 120 (floor 1) | 3,600 | 0 | Yes | Dry Food Storage |
| 121 (floor 1) | 3,800 | 0 | Yes | Beer & Soda |
| 164 | 5,750 | 0 | Freezer | Frozen Food |
| 176 | 7,800 | 0 | No | Dry Food Storage |
| 4 Milvans | 640 | 0 | Freezer | Frozen Food |
| Subtotal | 21,590 |  |  |  |
| ### Specialty Warehousing |  |  |  |  |
| 120 | 3,200 | 150 | Yes | IT Storage |
| 126 | 5,000 | 0 | Yes | SPSM |
| 174 | 2,000 | 0 | Yes | Flams |
| 168 | 4,000 | 0 | No | Auto Parts |
| 132 | 7,800 | 200 | Yes | Auto Parts |
| Subtotal | 22,000 | 350 |  |  |
| TOTAL | 124,990 | 2,700 |  |  |